## Project Data
Issue Type | Issue Key | Issue Id | Project ID | Status | Start Date | Due Date | Type | Hours Used | Hours Estimated | Row Labels | Count of Projects
Epic | CCC-1 | 11048 | Study 1 | To Do | 2023-06-06 | 2024-12-18 | Data Generation | 1122 | 1000 | Done | 3
Epic | CCC-14 | 11061 | Grant 1 | To Do | 2024-05-14 | 2024-12-27 | Grant | 797 | 1000 | To Do | 21
Epic | CCC-12 | 11059 | Workshop 1 | To Do | 2024-07-03 | 2024-12-28 | Health Equity | 716 | 750 | Grand Total | 24
Epic | CCC-21 | 11068 | Advisory Council | To Do | 2024-01-01 | 2024-12-31 | Education Project | 830 | 1000
Epic | CCC-13 | 11060 | Mentorship Pilot | To Do | 2024-07-01 | 2024-12-31 | Initiatives | 699 | 600
Epic | CCC-11 | 11058 | RWE Study 1 | To Do | 2024-07-03 | 2024-12-31 | Initiatives | 726 | 500
Epic | CCC-5 | 11052 | Biopsy Study | To Do | 2023-08-03 | 2024-12-31 | Grant | 811 | 1000
Epic | CCC-4 | 11051 | Diagnostic Study | To Do | 2024-07-31 | 2025-01-31 | Data Generation | 1154 | 1150
Epic | CCC-6 | 11053 | Collaborative Study 1 | To Do | 2024-04-01 | 2025-02-16 | Education Project | 670 | 500
Epic | CCC-15 | 11062 | Investigator Study 1 | To Do | 2024-05-23 | 2025-03-31 | Health Equity | 1043 | 1000
Epic | CCC-10 | 11057 | RWE Study 2 | To Do | 2024-07-01 | 2025-03-31 | Data Generation | 761 | 800
Epic | CCC-3 | 11050 | Collaborative Study 2 | To Do | 2022-11-30 | 2025-03-31 | Health Equity | 746 | 750
Epic | CCC-7 | 11054 | RWE Study 3 | To Do | 2024-07-03 | 2025-12-31 | Grant | 421 | 500
Epic | CCC-2 | 11049 | Investigator Study 2 | To Do | 2024-01-01 | 2025-12-31 | Grant | 70 | 75
Epic | CCC-95 | 11221 | Collaborative Study 3 | To Do | 2024-08-01 | 2026-04-04 | Education Project | 357 | 500
Epic | CCC-16 | 11063 | Investigator Study 3 | To Do | 2024-08-01 | 2026-08-31 | Education Project | 442 | 750
Epic | CCC-9 | 11056 | Investigator Study 4 | To Do | 2025-01-01 | 2026-12-31 | Data Generation | 906 | 1000
Epic | CCC-160 | 11365 | Education Campaign | Done | 2024-07-03 | 2025-12-31 | Grant | 380 | 500
Epic | CCC-156 | 11361 | Patient Journey 1 | Done | 2024-01-01 | 2025-12-31 | Initiatives | 281 | 500
Epic | CCC-131 | 11281 | Internal_Operations | To Do | 2024-08-01 | 2026-04-04 | Data Generation | 1011 | 1000
Epic | CCC-121 | 11269 | Collaborative Study 4 | Done | 2024-08-01 | 2026-08-31 | Data Generation | 450 | 500
Epic | CCC-109 | 11250 | Completed_Projects | To Do | 2025-01-01 | 2026-12-31 | Health Equity | 342 | 500
Epic | CCC-94 | 11220 | Collaborative Study 5 | To Do | 2024-12-15 | 2026-12-31 | Grant | 690 | 800
Epic | CCC-89 | 11166 | Study 2 | To Do | 2024-08-01 | 2026-08-31 | Grant | 130 | 150

## Task Health Data
Project ID | Task | Start | Due | Status | Late Start | Past Due | QC Check
Study 1 | Follow ups | 2023-06-06 | 2023-12-18 | Started |  | X | TRUE
Study 1 | Identify and Revaluate | 2023-06-07 | 2023-12-19 | Done |  | Checkmark | FALSE
Study 1 | Kick-Off | 2023-06-08 | 2023-12-20 | Done |  | Checkmark | TRUE
Grant 1 | April Recorded | 2024-05-14 | 2024-12-27 | Started |  | Checkmark | FALSE
Grant 1 | Build | 2024-05-15 | 2024-12-28 | Started |  | Checkmark | FALSE
Grant 1 | Validation | 2024-05-16 | 2024-12-29 | Started |  | Checkmark | FALSE
Workshop 1 | Configure | 2024-07-03 | 2024-12-28 | Not Started |  | Checkmark | TRUE
Workshop 1 | Training | 2024-07-04 | 2024-12-29 | Started |  | Checkmark | FALSE
Workshop 1 | Implement Procedure | 2024-07-05 | 2024-12-30 | Started |  | Checkmark | TRUE
Advisory Council | Core Resources | 2024-01-01 | 2024-12-31 | Started |  | Checkmark | TRUE
Advisory Council | Follow ups | 2024-01-02 | 2025-01-01 | Done |  | Checkmark | FALSE
Advisory Council | Identify and Revaluate | 2024-01-03 | 2025-01-02 | Done |  | Checkmark | TRUE
Mentorship Pilot | Kick-Off | 2024-07-01 | 2024-12-31 | Started |  | Checkmark | FALSE
Mentorship Pilot | April Recorded | 2024-07-02 | 2025-01-01 | Not Started |  | Checkmark | FALSE
Mentorship Pilot | Build | 2024-07-03 | 2025-01-02 | Done |  | Checkmark | FALSE
RWE Study 1 | Validation | 2024-07-03 | 2/31/2024 | Done |  | #VALUE! | TRUE
RWE Study 1 | Configure | 2024-07-04 | 2/31/2025 | Started |  | #VALUE! | FALSE
RWE Study 1 | Training | 2024-07-05 | 2/31/2026 | Started |  | #VALUE! | TRUE
Biopsy Study | Implement Procedure | 2023-08-03 | 2025-02-16 | Started |  | Checkmark | TRUE
Biopsy Study | Core Resources | 2023-08-04 | 2025-02-17 | Done |  | Checkmark | FALSE
Biopsy Study | Follow ups | 2023-08-05 | 2025-02-18 | Done |  | Checkmark | TRUE
Diagnostic Study | Identify and Revaluate | 2024-07-31 | 2025-03-31 | Started |  | Checkmark | TRUE
Diagnostic Study | Kick-Off | 2024-08-01 | 2025-04-01 | Not Started |  | Checkmark | TRUE
Diagnostic Study | April Recorded | 2024-08-02 | 2025-04-02 | Not Started |  | Checkmark | FALSE
Collaborative Study 1 | Build | 2024-04-01 | 2025-12-01 | Done |  | Checkmark | TRUE
Collaborative Study 1 | Validation | 2024-04-02 | 2025-12-02 | Done |  | Checkmark | TRUE
Collaborative Study 1 | Configure | 2024-04-03 | 2025-12-03 | Done |  | Checkmark | TRUE
Investigator Study 1 | Training | 2024-04-01 | 2026-08-31 | Done |  | Checkmark | FALSE
Investigator Study 1 | Implement Procedure | 2024-04-02 | 2026-09-01 | Done |  | Checkmark | TRUE
Investigator Study 1 | Core Resources | 2024-04-03 | 2026-09-02 | Done |  | Checkmark | TRUE
RWE Study 2 | Follow ups | 2024-05-23 | 2026-12-31 | Started |  | Checkmark | TRUE
RWE Study 2 | Identify and Revaluate | 2024-05-24 | 2027-01-01 | Started |  | Checkmark | FALSE
RWE Study 2 | Kick-Off | 2024-05-25 | 2027-01-02 | Started |  | Checkmark | TRUE
Collaborative Study 2 | April Recorded | 2024-07-01 | 2025-12-31 | Started |  | Checkmark | TRUE
Collaborative Study 2 | Build | 2024-07-02 | 2026-01-01 | Not Started |  | Checkmark | TRUE
Collaborative Study 2 | Validation | 2024-07-03 | 2026-01-02 | Started |  | Checkmark | FALSE
RWE Study 3 | Configure | 2024-07-03 | 2026-04-04 | Not Started |  | Checkmark | TRUE
RWE Study 3 | Training | 2024-07-04 | 2026-04-05 | Not Started |  | Checkmark | FALSE
RWE Study 3 | Implement Procedure | 2024-07-05 | 2026-04-06 | Not Started |  | Checkmark | TRUE
Investigator Study 2 | Core Resources | 2024-08-01 | 2026-08-31 | Not Started |  | Checkmark | FALSE
Investigator Study 2 | Follow ups | 2024-08-02 | 2026-09-01 | Started |  | Checkmark | TRUE
Investigator Study 2 | Identify and Revaluate | 2024-08-03 | 2026-09-02 | Started |  | Checkmark | FALSE
Collaborative Study 3 | Kick-Off | 2025-01-01 | 2026-12-31 | Not Started |  | Checkmark | FALSE
Collaborative Study 3 | April Recorded | 2025-01-02 | 2027-01-01 | Not Started |  | Checkmark | TRUE
Collaborative Study 3 | Build | 2025-01-03 | 2027-01-02 | Not Started |  | Checkmark | FALSE
Investigator Study 3 | Validation | 2024-01-01 | 2026-12-31 | Started |  | Checkmark | FALSE
Investigator Study 3 | Configure | 2024-01-02 | 2027-01-01 | Done |  | Checkmark | TRUE
Investigator Study 3 | Training | 2024-01-03 | 2027-01-02 | Done |  | Checkmark | FALSE
Investigator Study 4 | Implement Procedure | 2024-08-01 | 2026-08-31 | Not Started |  | Checkmark | FALSE
Investigator Study 4 | Core Resources | 2024-08-02 | 2026-09-01 | Not Started |  | Checkmark | TRUE
Investigator Study 4 | Follow ups | 2024-08-03 | 2026-09-02 | Not Started |  | Checkmark | FALSE
Education Campaign | Identify and Revaluate | 2025-01-01 | 2025-01-31 | Not Started |  | Checkmark | FALSE
Education Campaign | Kick-Off | 2025-01-02 | 2025-02-01 | Not Started |  | Checkmark | TRUE
Education Campaign | April Recorded | 2025-01-03 | 2025-02-02 | Not Started |  | Checkmark | FALSE
Patient Journey 1 | Build | 2024-12-15 | 2025-06-01 | Not Started |  | Checkmark | FALSE
Patient Journey 1 | Validation | 2024-12-16 | 2025-06-02 | Not Started |  | Checkmark | TRUE
Patient Journey 1 | Configure | 2024-12-17 | 2025-06-03 | Started |  | Checkmark | FALSE
Internal_Operations | Training | 2024-08-01 | 2025-08-01 | Done |  | Checkmark | FALSE
Internal_Operations | Implement Procedure | 2024-08-02 | 2025-08-02 | Done |  | Checkmark | TRUE
Internal_Operations | Core Resources | 2024-08-03 | 2025-08-03 | Done |  | Checkmark | FALSE
Collaborative Study 4 | [5 empty] | X
Collaborative Study 4 | [5 empty] | X
Collaborative Study 4 | [5 empty] | X
Completed_Projects | [5 empty] | X
Completed_Projects | [5 empty] | X
Completed_Projects | [5 empty] | X
Collaborative Study 5 | [5 empty] | X
Collaborative Study 5 | [5 empty] | X
Collaborative Study 5 | [5 empty] | X
Study 2 | [5 empty] | X
Study 2 | [5 empty] | X
Study 2 | [5 empty] | X
Formulas:
Past Due = IF(AND(TODAY() > [Due], [Status] <> "Done"), "X", IF(AND(TODAY() <= [Due], TODAY() >= [Due] - 5, [Status] <> "Done"), "Circle", "Checkmark"))

## Financials Data
Project ID | LT_Budget | Duration (mo) | Accrual Unit | Accrual # | Accrual to Date | Cash Out | Total Budget Used % | Cashout - Accrual | LT_Budget - Cashout | Max Budget | Milestone1 | Milestone2 | Milestone3 | Milestone4 | Milestone5 | Milestone6 | Milestone7 | Milestone8 | Milestone9 | Milestone10 | Total Completed | Q1 | Q2 | Q3 | Q4 | Total Possible | % Completed | MostRecentDate
Study 1 | 250000 | 18 | 13888.8889 | 12 | 166666.6667 | 72500 | 29% | -94166.6667 | 177500 | 2000000 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-08 | [6 empty] | 4 | 2 | 3 | 5 | 6 | 6 | 66.67% | 2023-07-08
Grant 1 | 100000 | 7 | 14285.7143 | 1 | 14285.7143 | 100000 | 100% | 85714.2857 | 0 | 2000000 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 |  |  |  |  | 6 | 1 | 3 | 4 | 6 | 6 | 100% | 2024-06-18
Workshop 1 | 450000 | 5 | 90000 | 0 | 0 | 211500 | 47% | 211500 | 238500 | 2000000 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 |  |  | 8 | 3 | 5 | 8 | 10 | 10 | 80% | 2024-08-09
Advisory Council | 250000 | 11 | 22727.2727 | 6 | 136363.6364 | 150000 | 60% | 13636.3636 | 100000 | 2000000 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 |  |  |  |  | 6 | 1 | 3 | 4 | 7 | 7 | 85.71% | 2024-02-05
Mentorship Pilot | 100000 | 5 | 20000 | 0 | 0 | 32000 | 32% | 32000 | 68000 | 2000000 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | [5 empty] | 5 | 2 | 3 | 5 | 6 | 6 | 83.33% | 2024-08-04
RWE Study 1 | 500000 | 5 | 100000 | 0 | 0 | 170000 | 34% | 170000 | 330000 | 2000000 | 2024-08-02 | 2024-08-03 | 2024-08-04 | [7 empty] | 3 | 1 | 2 | 3 |  | 3 | 100% | 2024-08-04
Biopsy Study | 628000 | 16 | 39250 | 11 | 431750 | 488431 | 77.78% | 56681 | 139569 | 2000000 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 |  |  |  |  | 6 | 3 | 5 | 6 | 7 | 7 | 85.71% | 2023-09-07
Diagnostic Study | 848000 | 6 | 141333.3333 | 0 | 0 | 339200 | 40% | 339200 | 508800 | 2000000 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 |  |  |  | 7 | 3 | 6 | 7 | 9 | 9 | 77.78% | 2024-09-05
Collaborative Study 1 | 700000 | 10 | 70000 | 3 | 210000 | 183000 | 26.14% | -27000 | 517000 | 2000000 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | [6 empty] | 4 | 2 | 4 | 6 | 8 | 8 | 50% | 2024-05-04
Investigator Study 1 | 500000 | 10 | 50000 | 1 | 50000 | 250000 | 50% | 200000 | 250000 | 2000000 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 |  |  |  |  | 6 | 2 | 5 | 7 | 10 | 10 | 60% | 2024-06-27
RWE Study 2 | 513000 | 8 | 64125 | 0 | 0 | 220590 | 43% | 220590 | 292410 | 2000000 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | [6 empty] | 4 | 1 | 3 | 4 | 5 | 5 | 80% | 2024-08-03
Collaborative Study 2 | 650000 | 28 | 23214.2857 | 19 | 441071.4286 | 325000 | 50% | -116071.4286 | 325000 | 2000000 | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | [5 empty] | 5 | 1 | 2 | 3 | 5 | 5 | 100% | 2023-01-03
RWE Study 3 | 1500000 | 17 | 88235.2941 | 0 | 0 | 585000 | 39% | 585000 | 915000 | 2000000 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | [6 empty] | 1 | 1 | 2 | 3 | 4 | 4 | 25% | 2024-08-05
Investigator Study 2 | 848000 | 23 | 36869.5652 | 6 | 221217.3913 | 305280 | 36% | 84062.6087 | 542720 | 2000000 | 2024-01-31 | 2024-02-01 | 2024-02-02 | [7 empty] | 3 | 1 | 2 | 3 | 5 | 5 | 60% | 2024-02-02
Collaborative Study 3 | 250000 | 20 | 12500 | 0 | 0 | 130000 | 52% | 130000 | 120000 | 2000000 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | [5 empty] | 5 | 2 | 3 | 5 | 8 | 8 | 62.5% | 2024-09-04
Investigator Study 3 | 500000 | 24 | 20833.3333 | 0 | 0 | 275000 | 55% | 275000 | 225000 | 2000000 | 2024-08-31 | 2024-09-01 | 2024-09-02 | [7 empty] | 3 | 3 | 6 | 8 | 9 | 9 | 33.33% | 2024-09-02
Investigator Study 4 | 2000000 | 23 | 86956.5217 | 0 | 0 | 1000000 | 50% | 1000000 | 1000000 | 2000000 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 |  |  |  | 4 | 1 | 4 | 6 | 10 | 10 | 40% | 2025-02-06
Education Campaign | 275000 | 17 | 16176.4706 | 0 | 0 | 132000 | 48% | 132000 | 143000 | 2000000 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | [6 empty] | 1 | 3 | 4 | 5 | 7 | 7 | 14.29% | 2024-08-05
Patient Journey 1 | 225000 | 23 | 9782.6087 | 6 | 58695.6522 | 72000 | 32% | 13304.3478 | 153000 | 2000000 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | [5 empty] | 5 | 1 | 2 | 3 | 6 | 6 | 83.33% | 2024-02-04
Internal_Operations | 525000 | 20 | 26250 | 0 | 0 | 194250 | 37% | 194250 | 330750 | 2000000 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 |  |  | 8 | 4 | 5 | 8 | 10 | 10 | 80% | 2024-09-02
Collaborative Study 4 | 325000 | 24 | 13541.6667 | 0 | 0 | 152750 | 47% | 152750 | 172250 | 2000000 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | [5 empty] | 5 | 1 | 2 | 4 | 6 | 6 | 83.33% | 2024-09-04
Completed_Projects | 575000 | 23 | 25000 | 0 | 0 | 189750 | 33% | 189750 | 385250 | 2000000 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 |  | 9 | 3 | 5 | 7 | 10 | 10 | 90% | 2025-02-08
Collaborative Study 5 | 750000 | 24 | 31250 | 0 | 0 | 360000 | 48% | 360000 | 390000 | 2000000 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | [6 empty] | 4 | 1 | 2 | 4 | 7 | 7 | 57.14% | 2025-01-17
Study 2 | 250000 | 24 | 10416.6667 | 0 | 0 | 65000 | 26% | 65000 | 185000 | 2000000 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 |  |  |  |  | 6 | 3 | 5 | 6 | 8 | 8 | 75% | 2024-09-05
Formulas:
Accrual # = IFERROR(DATEDIF(Projects[[#This Row],[Start Date]], TODAY(), "m"), 0)
Milestone1 = Projects[[#This Row],[Start Date]]+30
Milestone2 = Finances[[#This Row],[Milestone1]]+1
Milestone3 = Finances[[#This Row],[Milestone2]]+1
Milestone4 = Finances[[#This Row],[Milestone2]]+1
MostRecentDate = MAX('Project Data'!F2,[Milestone1]:[Milestone10])
Milestone7 = Finances[[#This Row],[Milestone6]]+1
Milestone8 = Finances[[#This Row],[Milestone7]]+1
Milestone9 = Finances[[#This Row],[Milestone8]]+1
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of months to date

## Feedback
Institution Name | Feedback Date | Feedback Type | Feedback Categories | Feedback Score | Qualitative Feedback
Institution 68 | 2024-03-11 | Interview | Cooperation | 3 | Feedback comment 68 | Row Labels | Average of Feedback Score
Institution 47 | 2023-08-02 | Interview | Cooperation | 2 | Feedback comment 47 | Communication | 1.925
Institution 62 | 2023-05-22 | Interview | Service Quality | 2 | Feedback comment 62 | Cooperation | 2.8182
Institution 90 | 2023-08-09 | Survey | Communication | 2 | Feedback comment 90 | Service Quality | 3.5926
Institution 80 | 2024-04-16 | Interview | Communication | 3 | Feedback comment 80 | Grand Total | 2.67
Institution 11 | 2023-08-01 | Survey | Communication | 3 | Feedback comment 11
Institution 60 | 2023-11-02 | Survey | Cooperation | 1 | Feedback comment 60
Institution 56 | 2024-03-10 | Survey | Communication | 2 | Feedback comment 56
Institution 6 | 2023-06-21 | Interview | Cooperation | 3 | Feedback comment 6
Institution 61 | 2023-11-06 | Interview | Communication | 1 | Feedback comment 61
Institution 16 | 2023-06-23 | Interview | Cooperation | 2 | Feedback comment 16
Institution 86 | 2024-03-12 | Survey | Communication | 1 | Feedback comment 86
Institution 88 | 2023-11-16 | Survey | Communication | 1 | Feedback comment 88
Institution 77 | 2024-02-21 | Survey | Cooperation | 2 | Feedback comment 77
Institution 19 | 2024-03-24 | Survey | Cooperation | 5 | Feedback comment 19
Institution 7 | 2024-03-06 | Interview | Service Quality | 5 | Feedback comment 7
Institution 93 | 2023-09-26 | Interview | Cooperation | 3 | Feedback comment 93
Institution 96 | 2023-05-11 | Survey | Cooperation | 1 | Feedback comment 96
Institution 74 | 2024-01-21 | Interview | Cooperation | 2 | Feedback comment 74
Institution 87 | 2023-10-11 | Survey | Service Quality | 1 | Feedback comment 87
Institution 31 | 2023-08-08 | Survey | Service Quality | 4 | Feedback comment 31
Institution 36 | 2024-01-07 | Interview | Cooperation | 5 | Feedback comment 36
Institution 38 | 2024-02-02 | Survey | Service Quality | 1 | Feedback comment 38
Institution 97 | 2023-04-21 | Interview | Communication | 3 | Feedback comment 97
Institution 35 | 2024-03-22 | Interview | Cooperation | 3 | Feedback comment 35
Institution 22 | 2023-12-19 | Survey | Cooperation | 3 | Feedback comment 22
Institution 75 | 2023-05-02 | Interview | Service Quality | 5 | Feedback comment 75
Institution 51 | 2023-11-24 | Survey | Communication | 3 | Feedback comment 51
Institution 49 | 2023-11-06 | Survey | Cooperation | 5 | Feedback comment 49
Institution 34 | 2024-04-19 | Survey | Communication | 2 | Feedback comment 34
Institution 84 | 2024-04-10 | Interview | Cooperation | 4 | Feedback comment 84
Institution 57 | 2024-01-20 | Interview | Communication | 2 | Feedback comment 57
Institution 72 | 2023-11-10 | Interview | Communication | 2 | Feedback comment 72
Institution 29 | 2023-06-09 | Interview | Cooperation | 3 | Feedback comment 29
Institution 4 | 2023-06-21 | Interview | Communication | 1 | Feedback comment 4
Institution 33 | 2024-03-03 | Interview | Service Quality | 4 | Feedback comment 33
Institution 10 | 2023-08-09 | Survey | Cooperation | 3 | Feedback comment 10
Institution 5 | 2023-08-01 | Interview | Service Quality | 4 | Feedback comment 5
Institution 25 | 2023-08-13 | Interview | Service Quality | 5 | Feedback comment 25
Institution 83 | 2024-01-28 | Interview | Communication | 1 | Feedback comment 83
Institution 58 | 2023-09-27 | Survey | Service Quality | 1 | Feedback comment 58
Institution 91 | 2023-11-24 | Survey | Service Quality | 4 | Feedback comment 91
Institution 71 | 2024-03-16 | Interview | Service Quality | 1 | Feedback comment 71
Institution 78 | 2023-10-16 | Survey | Communication | 3 | Feedback comment 78
Institution 70 | 2023-04-30 | Survey | Cooperation | 5 | Feedback comment 70
Institution 54 | 2023-08-23 | Interview | Communication | 1 | Feedback comment 54
Institution 13 | 2023-04-20 | Survey | Communication | 2 | Feedback comment 13
Institution 26 | 2023-09-16 | Survey | Communication | 2 | Feedback comment 26
Institution 95 | 2023-05-29 | Interview | Communication | 1 | Feedback comment 95
Institution 67 | 2023-06-11 | Interview | Communication | 1 | Feedback comment 67
Institution 3 | 2023-09-27 | Interview | Cooperation | 4 | Feedback comment 3
Institution 64 | 2023-07-20 | Interview | Communication | 1 | Feedback comment 64
Institution 21 | 2023-09-09 | Survey | Communication | 2 | Feedback comment 21
Institution 44 | 2024-02-10 | Survey | Communication | 3 | Feedback comment 44
Institution 43 | 2023-06-03 | Survey | Communication | 3 | Feedback comment 43
Institution 15 | 2023-10-24 | Interview | Cooperation | 1 | Feedback comment 15
Institution 46 | 2024-01-11 | Interview | Communication | 2 | Feedback comment 46
Institution 27 | 2024-03-22 | Interview | Communication | 2 | Feedback comment 27
Institution 82 | 2023-12-23 | Survey | Service Quality | 4 | Feedback comment 82
Institution 17 | 2023-11-14 | Survey | Communication | 2 | Feedback comment 17
Institution 28 | 2023-11-21 | Survey | Service Quality | 4 | Feedback comment 28
Institution 42 | 2023-12-30 | Survey | Communication | 2 | Feedback comment 42
Institution 8 | 2023-09-21 | Survey | Cooperation | 3 | Feedback comment 8
Institution 59 | 2024-02-17 | Survey | Communication | 2 | Feedback comment 59
Institution 40 | 2024-02-01 | Interview | Service Quality | 5 | Feedback comment 40
Institution 14 | 2023-09-18 | Survey | Service Quality | 3 | Feedback comment 14
Institution 48 | 2023-05-24 | Survey | Service Quality | 4 | Feedback comment 48
Institution 63 | 2023-08-15 | Survey | Cooperation | 3 | Feedback comment 63
Institution 85 | 2023-12-03 | Interview | Communication | 1 | Feedback comment 85
Institution 30 | 2024-02-05 | Survey | Service Quality | 5 | Feedback comment 30
Institution 73 | 2023-06-06 | Interview | Service Quality | 5 | Feedback comment 73
Institution 79 | 2023-12-25 | Interview | Communication | 3 | Feedback comment 79
Institution 81 | 2024-01-22 | Survey | Service Quality | 5 | Feedback comment 81
Institution 89 | 2024-03-14 | Interview | Service Quality | 5 | Feedback comment 89
Institution 1 | 2023-05-19 | Interview | Cooperation | 2 | Feedback comment 1
Institution 92 | 2024-01-22 | Survey | Cooperation | 2 | Feedback comment 92
Institution 50 | 2023-11-27 | Interview | Cooperation | 2 | Feedback comment 50
Institution 32 | 2023-05-23 | Interview | Cooperation | 1 | Feedback comment 32
Institution 2 | 2023-12-05 | Interview | Communication | 1 | Feedback comment 2
Institution 24 | 2023-05-19 | Survey | Communication | 2 | Feedback comment 24
Institution 52 | 2023-05-15 | Survey | Service Quality | 4 | Feedback comment 52
Institution 41 | 2024-03-14 | Survey | Communication | 1 | Feedback comment 41
Institution 69 | 2024-04-05 | Survey | Communication | 3 | Feedback comment 69
Institution 45 | 2023-07-10 | Survey | Service Quality | 1 | Feedback comment 45
Institution 94 | 2024-03-04 | Interview | Cooperation | 2 | Feedback comment 94
Institution 53 | 2023-06-29 | Interview | Communication | 2 | Feedback comment 53
Institution 20 | 2024-03-31 | Survey | Communication | 2 | Feedback comment 20
Institution 9 | 2023-12-27 | Survey | Communication | 2 | Feedback comment 9
Institution 100 | 2023-12-19 | Interview | Communication | 1 | Feedback comment 100
Institution 66 | 2023-08-07 | Survey | Cooperation | 3 | Feedback comment 66
Institution 98 | 2023-06-29 | Interview | Service Quality | 5 | Feedback comment 98
Institution 12 | 2024-02-21 | Survey | Cooperation | 3 | Feedback comment 12
Institution 65 | 2024-03-20 | Survey | Cooperation | 2 | Feedback comment 65
Institution 39 | 2024-02-01 | Survey | Communication | 3 | Feedback comment 39
Institution 23 | 2023-08-01 | Survey | Service Quality | 3 | Feedback comment 23
Institution 76 | 2023-08-20 | Survey | Cooperation | 5 | Feedback comment 76
Institution 37 | 2024-02-11 | Survey | Cooperation | 4 | Feedback comment 37
Institution 55 | 2023-09-26 | Survey | Cooperation | 1 | Feedback comment 55
Institution 99 | 2024-02-10 | Interview | Service Quality | 5 | Feedback comment 99
Institution 18 | 2023-09-16 | Survey | Service Quality | 2 | Feedback comment 18

## Icons
RISK ICONS | [5 empty] | ▮ | ▯ | https://www.posterpresentations.com/alt-code-cheatsheet.html
▯▯▯▯▯ | ▮▯▯▯▯ | ▮▮▯▯▯ | ▮▮▮▯▯ | ▮▮▮▮▯ | ▮▮▮▮▮
Emoji based Icon sets == Win + . OR Win + ;
PM Defined Status ICONS
75% | 4 | ⦿ | ✓
50% | 3 | ⦿ | ●
25% | 2 | ⦿ | ✖
0% | 1 | ⦿
|  | Issue Icons |  | ‼
| Low | ↘ | Down
| Med | →
| High | ↗ | Up | ↘️
| Critical | ⚠️ | Stop

## DateDiffs
Project ID | Days from Today
Study 1 | -168
Grant 1 | -177
Workshop 1 | -178
Advisory Council | -181
Mentorship Pilot | -181
RWE Study 1 | -181
Biopsy Study | -181
Diagnostic Study | -212
Collaborative Study 1 | -228
Investigator Study 1 | -271
RWE Study 2 | -271
Collaborative Study 2 | -271
RWE Study 3 | -546
Investigator Study 2 | -546
Collaborative Study 3 | -640
Investigator Study 3 | -789
Investigator Study 4 | -911
Education Campaign | -546
Patient Journey 1 | -546
Internal_Operations | -640
Collaborative Study 4 | -789
Completed_Projects | -911
Collaborative Study 5 | -911
Study 2 | -789

## Funnel
Project Status | Conversions
L1 | 76
L2 | 55
L3 | 40
Launch | 20

## Project Types
Bar chart type | Count
Grant | 7
Data Generation | 6
Education Project | 4
Initiatives | 3
Health Equity | 4

## PM Defined Status
Project ID | Scope Bin | Scope | Schedule | Budget | OVERALL | Bin | Total Possible | Segments | Red | Yellow | Green | Gray | Total
Study 1 | 3 | 2 | 1 | 1 | 1 | 3 | 6 | Overall | 4 | 12 | 4 | 0 | 20
Grant 1 | 4 | 1 | 1 | 3 | 2 | 4 | 6 | Scope | 8 | 2 | 9 | 0 | 19
Workshop 1 | 4 | 1 | 1 | 1 | 1 | 4 | 10 | Schedule | 5 | 5 | 10 | 0 | 20
Advisory Council | 4 | 1 | 1 | 2 | 1 | 4 | 7 | Budget | 11 | 4 | 5 | 0 | 20
Mentorship Pilot | 4 | 1 | 1 | 1 | 1 | 4 | 6
RWE Study 1 | 4 | 1 | 1 | 1 | 1 | 4 | 3
Biopsy Study | 4 | 1 | 1 | 3 | 2 | 4 | 7
Diagnostic Study | 4 | 1 | 1 | 1 | 1 | 4 | 9
Collaborative Study 1 | 2 | 3 | 1 | 1 | 2 | 2 | 8
Investigator Study 1 | 3 | 2 | 1 | 1 | 1 | 3 | 10
RWE Study 2 | 4 | 1 | 1 | 1 | 1 | 4 | 5
Collaborative Study 2 | 4 | 1 | 1 | 1 | 1 | 4 | 5
RWE Study 3 | 1 | 3 | 1 | 1 | 2 | 1 | 4
Investigator Study 2 | 3 | 2 | 1 | 1 | 1 | 3 | 5
Collaborative Study 3 | 3 | 2 | 1 | 2 | 2 | 3 | 8
Investigator Study 3 | 2 | 3 | 1 | 2 | 2 | 2 | 9
Investigator Study 4 | 2 | 3 | 1 | 1 | 2 | 2 | 10
Education Campaign | 1 | 3 | 1 | 1 | 2 | 1 | 7
Patient Journey 1 | 4 | 1 | 1 | 1 | 1 | 4 | 6
Internal_Operations | 4 | 1 | 1 | 1 | 1 | 4 | 10
Collaborative Study 4 | 4 | 1 | 1 | 1 | 1 | 4 | 6
Completed_Projects | 4 | 1 | 1 | 1 | 1 | 4 | 10
Collaborative Study 5 | 3 | 2 | 1 | 1 | 1 | 3 | 7
Study 2 | 3 | 2 | 1 | 1 | 1 | 3 | 8

## Gauges
Donut | Total Budget | Current Spend | Total Status | Current Status
30 | 13512000 | 6003251 | 75 | 32
40
30
100

## Total Risk
Project ID | Pace | Execution | Resources | Total | unique identifier
Project 01 | 34 | 16 | 20 | 70 | 70 | [5 empty] | Pace | Execution | Resouces
Project 02 | 12 | 13 | 0 | 25 | 25 | [5 empty] | #REF! | #REF! | #REF!
Project 03 | 27 | 9 | 12 | 48 | 48
Project 04 | 35 | 20 | 0 | 55 | 55.0001
Project 05 | 46 | 29 | 3 | 78 | 78.0001 | RISK |  |  |  | Total Risk Sum
Project 06 | 23 | 8 | 19 | 50 | 50.0001
Project 07 | 2 | 26 | 1 | 29 | 29.0001 |  | Boxes |  | Categories
Project 08 | 15 | 12 | 10 | 37 | 37.0001 |  | 0 | ▯▯▯▯▯ | Pace
Project 09 | 6 | 26 | 2 | 34 | 34.0001 |  | 1 | ▮▯▯▯▯ | Execute
Project 10 | 10 | 36 | 8 | 54 | 54.0001 |  | 2 | ▮▮▯▯▯ | Resource
Project 11 | 0 | 12 | 2 | 14 | 14.0001 |  | 3 | ▮▮▮▯▯
Project 12 | 3 | 6 | 12 | 21 | 21.0001 |  | 4 | ▮▮▮▮▯
Project 13 | 8 | 31 | 16 | 55 | 55.0001 |  | 5 | ▮▮▮▮▮
Project 14 | 25 | 1 | 20 | 46 | 46.0001
Project 15 | 12 | 14 | 21 | 47 | 47.0002
Project 16 | 5 | 16 | 3 | 24 | 24.0002 | Severity Score
Project 17 | 15 | 3 | 8 | 26 | 26.0002 | Range (low) | Range (high)
Project 18 | 5 | 4 | 10 | 19 | 19.0002 | 0 | 1 | -
Project 19 | 2 | 4 | 8 | 14 | 14.0002 | 1 | 10 | L
Project 20 | 4 | 1 | 22 | 27 | 27.0002 | 10 | 20 | M
Average | 14.45 | 14.35 | 9.85 | 38.65 | 38.6502 | 20 | 30 | H
[6 empty] | 30 | 40 | C

## Resources Risk
Project ID | Risk Description | Probability | Impact | Risk Score
Project 01 | Budget Overruns | 1 | 4 | 4
Project 01 | Fluctuating Exchange Rates | 2 | 2 | 4
Project 01 | Inflationary Pressures | 4 | 3 | 12
Project 03 | Funding Interruption | 3 | 4 | 12
Project 05 | Material Shortages | 1 | 3 | 3
Project 06 | Budget Overruns | 1 | 4 | 4
Project 06 | Fluctuating Exchange Rates | 5 | 3 | 15
Project 07 | Inflationary Pressures | 1 | 1 | 1
Project 08 | Funding Interruption | 5 | 2 | 10
Project 09 | Material Shortages | 2 | 1 | 2
Project 10 | Budget Overruns | 4 | 2 | 8
Project 11 | Fluctuating Exchange Rates | 2 | 1 | 2
Project 12 | Inflationary Pressures | 3 | 4 | 12
Project 13 | Funding Interruption | 5 | 2 | 10
Project 13 | Material Shortages | 2 | 3 | 6
Project 14 | Budget Overruns | 4 | 5 | 20
Project 15 | Fluctuating Exchange Rates | 4 | 2 | 8
Project 15 | Inflationary Pressures | 1 | 1 | 1
Project 15 | Funding Interruption | 3 | 4 | 12
Project 16 | Material Shortages | 3 | 1 | 3
Project 17 | Budget Overruns | 4 | 2 | 8
Project 18 | Fluctuating Exchange Rates | 5 | 2 | 10
Project 19 | Inflationary Pressures | 5 | 1 | 5
Project 19 | Funding Interruption | 3 | 1 | 3
Project 20 | Material Shortages | 2 | 3 | 6
Project 20 | Budget Overruns | 4 | 3 | 12
Project 20 | Fluctuating Exchange Rates | 1 | 4 | 4

## Pace Risk
Project ID | Risk Description | Probability | Impact | Risk Score
Project 01 | Unforeseen Regulatory Changes | 4 | 4 | 16
Project 01 | Dependency Delays | 5 | 3 | 15
Project 01 | Permitting Issues | 3 | 1 | 3
Project 02 | Resource Allocation Delays | 3 | 3 | 9
Project 02 | Vendor Delivery Issues | 1 | 2 | 2
Project 02 | Unforeseen Regulatory Changes | 1 | 1 | 1
Project 03 | Dependency Delays | 4 | 4 | 16
Project 03 | Permitting Issues | 1 | 1 | 1
Project 03 | Resource Allocation Delays | 5 | 2 | 10
Project 04 | Vendor Delivery Issues | 4 | 5 | 20
Project 04 | Unforeseen Regulatory Changes | 5 | 1 | 5
Project 04 | Dependency Delays | 5 | 2 | 10
Project 05 | Permitting Issues | 3 | 5 | 15
Project 05 | Resource Allocation Delays | 3 | 5 | 15
Project 05 | Vendor Delivery Issues | 4 | 4 | 16
Project 06 | Unforeseen Regulatory Changes | 1 | 3 | 3
Project 06 | Dependency Delays | 4 | 3 | 12
Project 06 | Permitting Issues | 4 | 2 | 8
Project 07 | Resource Allocation Delays | 1 | 2 | 2
Project 08 | Vendor Delivery Issues | 3 | 5 | 15
Project 09 | Unforeseen Regulatory Changes | 2 | 3 | 6
Project 10 | Dependency Delays | 2 | 2 | 4
Project 10 | Permitting Issues | 2 | 3 | 6
Project 12 | Unforeseen Regulatory Changes | 3 | 1 | 3
Project 13 | Dependency Delays | 2 | 4 | 8
Project 14 | Permitting Issues | 5 | 5 | 25
Project 15 | Resource Allocation Delays | 3 | 4 | 12
Project 16 | Vendor Delivery Issues | 1 | 5 | 5
Project 17 | Unforeseen Regulatory Changes | 5 | 3 | 15
Project 18 | Dependency Delays | 1 | 5 | 5
Project 19 | Permitting Issues | 1 | 2 | 2
Project 20 | Resource Allocation Delays | 4 | 1 | 4

## Execution Risk
Project ID | Risk Description | Probability | Impact | Risk Score
Project 01 | Technical Failures | 4 | 4 | 16
Project 02 | Scope Creep | 2 | 4 | 8
Project 02 | Quality Control Failures | 1 | 5 | 5
Project 03 | Team Turnover | 3 | 1 | 3
Project 03 | Inadequate Team Skills | 3 | 2 | 6
Project 04 | Technical Failures | 4 | 5 | 20
Project 05 | Scope Creep | 2 | 2 | 4
Project 05 | Quality Control Failures | 5 | 1 | 5
Project 05 | Team Turnover | 5 | 4 | 20
Project 06 | Inadequate Team Skills | 4 | 2 | 8
Project 07 | Technical Failures | 5 | 5 | 25
Project 07 | Scope Creep | 1 | 1 | 1
Project 08 | Quality Control Failures | 4 | 3 | 12
Project 09 | Team Turnover | 5 | 4 | 20
Project 09 | Inadequate Team Skills | 2 | 3 | 6
Project 10 | Technical Failures | 2 | 5 | 10
Project 10 | Scope Creep | 2 | 5 | 10
Project 10 | Quality Control Failures | 4 | 4 | 16
Project 11 | Team Turnover | 2 | 1 | 2
Project 11 | Inadequate Team Skills | 5 | 2 | 10
Project 12 | Technical Failures | 3 | 2 | 6
Project 13 | Scope Creep | 2 | 3 | 6
Project 13 | Technical Failures | 5 | 5 | 25
Project 14 | Scope Creep | 1 | 1 | 1
Project 15 | Quality Control Failures | 2 | 5 | 10
Project 15 | Team Turnover | 2 | 2 | 4
Project 16 | Inadequate Team Skills | 4 | 4 | 16
Project 17 | Technical Failures | 3 | 1 | 3
Project 18 | Scope Creep | 2 | 2 | 4
Project 19 | Quality Control Failures | 2 | 2 | 4
Project 20 | Team Turnover | 1 | 1 | 1

## Ext. Feedback
Math for graphics
Communication | #REF! | 5 | #REF! | #REF! | #REF!
Cooperation | #REF! | 5 | #REF! | #REF! | #REF!
Service Qualtiy | #REF! | 5 | #REF! | #REF! | #REF!
Look into making half circle donuts for gauges

## Issues
Project ID | Issue Description | Severity | Count | Score | Bin | Lookup | Project ID | Sum of Score | Sum of Count
Study 1 | Vendor submitted data late | Low | 2 | 2 | L | L | Advisory Council | 10 | 1
Grant 1 | Deadline Miss | Med | 1 | 2 | L | L | Biopsy Study | 2 | 2
Workshop 1 | Resource Shortage | High | 3 | 12 | H | M | Collaborative Study 1 | 10 | 1 | Severity | Weight
Advisory Council | Fraudulent Data | Critical | 1 | 10 | H | M | Collaborative Study 2 | 4 | 1 | Low | 1
Mentorship Pilot | Technical Challenges | Med | 1 | 2 | L | L | Collaborative Study 3 | 10 | 1 | Med | 2
RWE Study 1 | Quality Issues | High | 3 | 12 | H | M | Collaborative Study 4 | 1 | 1 | High | 4
Biopsy Study | Software Bugs | Low | 2 | 2 | L | L | Collaborative Study 5 | 2 | 1 | Critical | 10
Diagnostic Study | Vendor Delay | Low | 1 | 1 | L | - | Completed_Projects | 8 | 2
Collaborative Study 1 | Legal Issues | Critical | 1 | 10 | H | M | Diagnostic Study | 1 | 1 | Severity Score
Investigator Study 1 | Communication Breakdown | Low | 1 | 1 | L | - | Education Campaign | 1 | 1 | Range (low) | Range (high)
RWE Study 2 | Software Bugs | Med | 2 | 4 | M | L | Grant 1 | 2 | 1 | 0 | 1 | -
Collaborative Study 2 | Leadership Turnover | High | 1 | 4 | M | L | Internal_Operations | 20 | 2 | 1 | 3 | L
RWE Study 3 | Data Loss | High | 2 | 8 | M | M | Investigator Study 1 | 1 | 1 | 4 | 9 | M
Investigator Study 2 | Team Conflict | Low | 4 | 4 | M | L | Investigator Study 2 | 4 | 4 | 10 | 15 | H
Collaborative Study 3 | Planning Errors | Critical | 1 | 10 | H | M | Investigator Study 3 | 2 | 1 | 15 | 1000 | C
Investigator Study 3 | Weather Delay | Med | 1 | 2 | L | L | Investigator Study 4 | 4 | 2
Investigator Study 4 | hardware Failures | Med | 2 | 4 | M | L | Mentorship Pilot | 2 | 1
Education Campaign | Stakeeholder Disengagement | Low | 1 | 1 | L | - | Patient Journey 1 | 16 | 4
Patient Journey 1 | Scope Creep | High | 4 | 16 | C | H | RWE Study 1 | 12 | 3
Internal_Operations | Deadline Miss | Critical | 2 | 20 | C | H | RWE Study 2 | 4 | 2
Collaborative Study 4 | Change Resistance | Low | 1 | 1 | L | - | RWE Study 3 | 8 | 2 | =MATCH([@Score],$S$18:$S$22,1)
Completed_Projects | Misaligned Objectives | High | 2 | 8 | M | M | Study 1 | 2 | 2
Collaborative Study 5 | Software Bugs | Med | 1 | 2 | L | L | Study 2 | 4 | 2
Study 2 | Scope Creep | Med | 2 | 4 | M | L | Workshop 1 | 12 | 3
[7 empty] | Grand Total | 142 | 42

## Project Status
Project Status
Not Started | ▮ Not Started | Total project count | 20
In Progress | ▮ In Progress | Projects Overdue | 3
On Hold | ▮ On Hold
At Risk | ▮ At Risk
Completed | ▮ Completed
Overdue | ▮ Overdue
Cancelled | ▮ Cancelled
Project ID | Project Status | Projects by PM Defined Status
Project 01 | Not Started | Segments | Red | Yellow | Green | Gray | Total
Project 02 | In Progress | Overall | #REF! | #REF! | #REF! | #REF! | #REF!
Project 03 | On Hold | Scope | #REF! | #REF! | #REF! | #REF! | #REF!
Project 04 | At Risk | Schedule | #REF! | #REF! | #REF! | #REF! | #REF!
Project 05 | Overdue | Budget | #REF! | #REF! | #REF! | #REF! | #REF!
Project 06 | Completed
Project 07 | Cancelled
Project 08 | Not Started
Project 09 | In Progress
Project 10 | On Hold
Project 11 | At Risk
Project 12 | Completed
Project 13 | Overdue
Project 14 | Cancelled
Project 15 | Not Started
Project 16 | In Progress
Project 17 | On Hold
Project 18 | At Risk
Project 19 | Completed
Project 20 | Overdue